## Sheet1
What went well | What went poorly | What ideas do you have | How should we take action
MRI dataset was successfully preprocessed and augmented. | Faced difficulty in integrating segmented output from U-Net into EfficientNet input. | Automate preprocessing pipeline to save time for future experiments. | Finalize and modularize the preprocessing code and maintain it in a shared repository.
U-Net architecture was implemented and achieved accurate segmentation results. | GPU limitations caused training delays. | Use cloud-based GPU platforms like Google Colab Pro or Kaggle kernels for faster training. | Allocate budget or plan usage for cloud GPU resources in advance.
EfficientNet model showed promising accuracy in classification. | Hyperparameter tuning took longer than expected due to inconsistent performance. | Explore hybrid models or ensemble methods to improve classification performance. | Schedule dedicated sprint days for model tuning and evaluation with clear benchmarks.
Team members coordinated well and followed agile timelines. | A few discussions were not on time because of different schedules | Time managemnet | Scheduled time weekly and maintaining a task update google sheet that can be used by both
Segmentation masks improved classification by focusing on lesion areas. | Initial segmentation outputs required post-processing to remove noise. | Add morphological filtering in segmentation pipeline. | Apply Gaussian smoothing and thresholding after segmentation.
Weekly stand-ups ensured regular progress updates and early issue detection. | Lack of real-time performance metrics during training phases. | Integrate TensorBoard for real-time performance monitoring. | Use TensorBoard callback in training scripts for every model run.